## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | teamd_2181_swen_261_13
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | JW 10/10/2018
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | JW 10/10/2018
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | JW 10/10/2018
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | JW 10/10/2018
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | JW 10/10/2018
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | JW 10/10/2018
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | JW 10/10/2018
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | JW 10/10/2018
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | JW 10/10/2018
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | JW 10/14/18
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | JW 10/14/18
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Fail | JW 10/14/2018 error message not shown on home
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | JW 10/14/18
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | JW 10/14/18
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | JW 10/14/18
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | JW 10/14/18
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | JW 10/14/18
As a Piece I want to be able to move so that the Player does not lose the game | Give I am a single piece when I do not have a jump available then I can make a simple forward move |  |  | Pass | JW 11/6/18
| Given I am a king piece when I do not have a jump available then I can make a simple forward or backwards move |  |  | Pass | JW 11/6/18
| Give that I have a jump available when it is my Player's turn then I must make a jump |  |  | Pass | JW 11/6/19
| Given that I have made a jump when I still have another jump available I must take it |  |  | Pass | JW 11/6/20
As a Player I want to be able to change turns so that I may make a move | Given I am in a game when an opponent successfully submits their move then I expect to gain the ability to make moves |  |  | Pass | JW 11/6/18
| Given I am in a game when it is not my turn then I expect to wait for my turn without error |  |  | Pass | JW 11/6/18
As a Player I want to be able to win or lose a game so that I may start another game | Given I am in a game when I have no moves then I expect my opponent to win the game and I lose |  |  | Pass | JW 11/6/18
| Given I am in a game when an opponent resigns the I should win the game and they should lose |  |  | Pass | JW 11/6/18
| Given I am in a game when I win or lose then I should be able to play a new game |  |  | Pass | JW 11/6/18
As a Player I want to be able to resign a game so that I may stop playing my current game | Given I am in a game when I resign then I should be able to start a new game |  |  | Pass | JW 11/6/18
As a Piece I want to be able to capture other pieces by means of jumping them in order to gain an advantage in the game. | Given I have made a valid move when I submit that move then all pieces jumped over should be removed from play |  |  | Pass | JW 11/6/18
As a Player I want to be able to back up my last move so that I do not have to commit to every move I sample | Given I have made a valid move when I back up then I expect to return to the starting position of that move |  |  | Pass | JW 11/6/18
As a Piece I want to be able to be kinged in order to make backwards moves | Given I am a single piece when I reach the king-line then I expect to be promoted to a king piece |  |  | Pass | JW 11/6/18
| Given I am a single piece when I am kinged then I expect my turn to end |  |  | Pass | JW 11/6/18
As a Player I want to be able to play a game against an AI opponent so that I do not have to wait for a non computer Player to join. | Given I have signed in when I reach the home screen then I expect to see an AI Player to start a game with
As an AI Player I want to be able to make a move so that I do not lose the game | Given a Player has started a game with me when it is my turn then I should be able to make a move
Given I am in a game when it is my turn and I have no moves I should lose the game
As a Player I want to be able to record a game so that I may play it back later | Given I am in a game when I make a move then I expect it to be recorded
Given I am in a game when I make an invalid move or back up then I dont expect to record that move
As a Player I want to be able to watch a previously recorded game to improve my playing abilities | Given I have completed a game when I return to the home screen then I expect to be able to replay that game